GOVERNMENT OF INDIA / EASTERN COALFIELDS LIMITED

| FROM | MoEFCC Regional Office, Bhubaneswar (Internal Tracking Note — ECL Project Team) |
| --- | --- |
| TO | Director (Projects), Eastern Coalfields Limited, Sanctoria [INTERNAL] |
| DATE | March 5, 2024 |
| STATUS | PENDING |

SUBJECT: PENDING: Forest Clearance Application — Kranti OCP Phase II (No Response from MoEFCC as of September 30, 2026)

Sir/Madam,

INTERNAL TRACKING NOTE — This document records the status of ECL's Forest Clearance application (Ref: ECL/FC/KROCP/2024/01 dated March 1, 2024) submitted to MoEFCC for Kranti OCP Phase II expansion.

As of September 30, 2026, the Ministry of Environment, Forest and Climate Change (MoEFCC) has NOT responded to the above application. The application has been pending for 579 days with no Stage-I clearance communication, no acknowledgement of deficiency, and no request for additional information received from MoEFCC.

Follow-up communications sent by ECL on: March 5, 2024 (acknowledgement request); June 15, 2024 (reminder); November 8, 2024 (escalation to ADG level); March 20, 2025 (reminder to Regional Office, Bhubaneswar). No response received to any.

STATUS: BOTTLENECK — This is the critical path item blocking Phase II expansion. Days pending as on September 30, 2026: 579 days. Escalation to Secretary (Forests), MoEFCC is recommended immediately.

Yours faithfully,

(Authorised Signatory)

MoEFCC Regional Office, Bhubaneswar (Internal Tracking Note — ECL Project Team)

Date: March 5, 2024